## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Milestone | Labels | Functions/Screens
Docs foundation | fix: docs foundation (commit 94aebd8, GymMaster-Frontend, 2026-06-01) | 1 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/94aebd8 | Close | Quang Anh | iter1 | bug
Align trainer notes links to /member/notes route to fix 404s | fix(fe-member): align trainer notes links to /member/notes route to fix 404s (commit 6ff03b3, GymMaster-Frontend, 2026-06-03) | 2 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/6ff03b3 | Close | Quang Anh | iter1 | bug | Member Dashboard [SCR-MEM-01]
Sidebar, workout form, bmi calculator, etc. add animations | fix sidebar, workout form, bmi calculator, etc. add animations (commit 89f4a66, GymMaster-Frontend, 2026-06-04) | 3 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/89f4a66 | Close | Quang Anh | iter1 | bug
Spotlight filter | fix spotlight filter (commit 4204b7a, GymMaster-Frontend, 2026-06-04) | 4 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/4204b7a | Close | Quang Anh | iter1 | bug
Sync URL hash '#add-meal' with MealJournalWorkspace active view state | fix(fe-nutrition): sync URL hash '#add-meal' with MealJournalWorkspace active view state (commit 18b27f0, GymMaster-Frontend, 2026-06-04) | 5 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/18b27f0 | Close | Quang Anh | iter1 | bug | Meal Journal [SCR-MEM-07]
Remove hardcoding userID in api | fix: remove hardcoding userID in api (commit d8eec17, GymMaster-Frontend, 2026-06-09) | 6 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/d8eec17 | Close | Quang Anh | iter1 | bug
Align check_ins column with code + add 006 spec5 incremental | fix(db): align check_ins column with code + add 006 spec5 incremental (commit c474f5b, GymMaster-backend, 2026-06-18) | 7 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/c474f5b | Close | Như | iter2 | documentation
Gui mealType dang byte cho backend (sua loi them bua an) | fix(fe-nutrition): gui mealType dang byte cho backend (sua loi them bua an) (commit f7e3568, GymMaster-Frontend, 2026-06-23) | 8 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/f7e3568 | Close | Như | iter2 | bug | Meal Journal [SCR-MEM-07]
Map package isActive (boolean) tu backend that | fix(fe-billing): map package isActive (boolean) tu backend that (commit e35844d, GymMaster-Frontend, 2026-06-23) | 9 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/e35844d | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
Unwrap paged /memberships response (sua loi search Sell Package) | fix(fe-billing): unwrap paged /memberships response (sua loi search Sell Package) (commit 6128564, GymMaster-Frontend, 2026-06-23) | 10 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/6128564 | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
Hien ro goi pending chua kich hoat (chua "tu nhan goi") | fix(fe-member): hien ro goi pending chua kich hoat (chua "tu nhan goi") (commit eec0d85, GymMaster-Frontend, 2026-06-24) | 11 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/eec0d85 | Close | Như | iter2 | bug | Member Dashboard [SCR-MEM-01]
Chuan hoa enum status tu backend (PascalCase -> snake_case) | fix(fe-billing): chuan hoa enum status tu backend (PascalCase -> snake_case) (commit 293b884, GymMaster-Frontend, 2026-06-24) | 12 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/293b884 | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
Roster don pending qua 10 phut -> "Da huy" | fix(fe-billing): roster don pending qua 10 phut -> "Da huy" (commit 0e995f7, GymMaster-Frontend, 2026-06-25) | 13 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/0e995f7 | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
GetPayments boc paged {items} (sua loi admin Nhat ky thanh toan) | fix(fe-billing): getPayments boc paged {items} (sua loi admin Nhat ky thanh toan) (commit 917e4be, GymMaster-Frontend, 2026-06-25) | 14 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/917e4be | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
Man khoa hien trong layout (co sidebar) + doi nav "Trang chu" | fix(fe-member): man khoa hien trong layout (co sidebar) + doi nav "Trang chu" (commit d21b47e, GymMaster-Frontend, 2026-06-25) | 15 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/d21b47e | Close | Như | iter2 | bug | Member Dashboard [SCR-MEM-01]
Hien ly do that khi ghi nhan that bai + chan don trung | fix(fe-billing): hien ly do that khi ghi nhan that bai + chan don trung (commit 445759f, GymMaster-Frontend, 2026-06-25) | 16 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/445759f | Close | Như | iter2 | bug | Membership Management [SCR-ADM-08]
Tu lam moi access token khi gap 401 roi retry | fix(fe-auth): tu lam moi access token khi gap 401 roi retry (commit 4f2aaca, GymMaster-Frontend, 2026-06-25) | 17 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/4f2aaca | Close | Như | iter2 | bug | Login [SCR-AUTH-02]
Gia han gui dung method + xu ly atomic active+paid | fix(fe-staff): gia han gui dung method + xu ly atomic active+paid (commit 0055e29, GymMaster-Frontend, 2026-06-25) | 18 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/0055e29 | Close | Như | iter2 | bug | Staff Dashboard [SCR-STF-01]
Sua mat khau demo dung voi seeder o man welcome/about | fix(fe-auth): sua mat khau demo dung voi seeder o man welcome/about (commit 108385a, GymMaster-Frontend, 2026-06-26) | 19 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/108385a | Close | Như | iter2 | bug | Login [SCR-AUTH-02]
Gui multipart cho scan-image (sua loi 415 khi quet anh AI) | fix(fe-nutrition): gui multipart cho scan-image (sua loi 415 khi quet anh AI) (commit a783653, GymMaster-Frontend, 2026-06-26) | 20 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/a783653 | Close | Như | iter2 | bug | Meal Journal [SCR-MEM-07]
Bo du lieu mock o dashboard, chi dung so lieu that | fix(fe-admin): bo du lieu mock o dashboard, chi dung so lieu that (commit 999d3f4, GymMaster-Frontend, 2026-06-26) | 21 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/999d3f4 | Close | Như | iter2 | bug | Admin Dashboard [SCR-ADM-01]
Dashboard le tan dung du lieu that + invalidate cheo (het phai F5) | fix(fe): dashboard le tan dung du lieu that + invalidate cheo (het phai F5) (commit b7d6eec, GymMaster-Frontend, 2026-06-26) | 22 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/b7d6eec | Close | Như | iter2 | bug
Chi mo khoa tinh nang khi goi ACTIVE (khong unlock khi pending) | fix(fe-member): chi mo khoa tinh nang khi goi ACTIVE (khong unlock khi pending) (commit e5d07fc, GymMaster-Frontend, 2026-06-26) | 23 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/e5d07fc | Close | Như | iter2 | bug | Member Dashboard [SCR-MEM-01]
Payment current-membership + lich su trung thuc + calo theo BE/GMT+7 (spec 003/006/007/010) | fix(part-y): payment current-membership + lich su trung thuc + calo theo BE/GMT+7 (spec 003/006/007/010) (commit 0cfaea9, GymMaster-Frontend, 2026-06-26) | 24 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/0cfaea9 | Close | Lộc | iter2 | documentation | Membership and VNPay [SCR-MEM-02]
Them MembershipExpiryBanner de sua import treo (build TS2307) | fix(fe-nutrition): them MembershipExpiryBanner de sua import treo (build TS2307) (commit f4209e0, GymMaster-Frontend, 2026-06-26) | 25 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/f4209e0 | Close | Lộc | iter2 | bug | Meal Journal [SCR-MEM-07]
Payment current-membership + lich su trung thuc + clock GMT+7 (spec 003/006/007/010) | fix(part-y): payment current-membership + lich su trung thuc + clock GMT+7 (spec 003/006/007/010) (commit 7eef3c0, GymMaster-backend, 2026-06-26) | 26 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/7eef3c0 | Close | Lộc | iter2 | documentation | Membership and VNPay [SCR-MEM-02]
ConfirmPayment tai dung payment Pending chong thu 2 lan (spec 003) | fix(be-membership): ConfirmPayment tai dung payment Pending chong thu 2 lan (spec 003) (commit 665364f, GymMaster-backend, 2026-06-26) | 27 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/665364f | Close | Lộc | iter2 | documentation | Sell Package [SCR-STF-03]
Doi cau chu canh bao phan cong PT cho than thien | fix(fe-pt): doi cau chu canh bao phan cong PT cho than thien (commit 687f109, GymMaster-Frontend, 2026-06-28) | 28 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/687f109 | Close | Như | iter2 | bug | PT Assignment [SCR-ADM-10]
PT check-in flow | Fix PT check-in flow (commit bd1b040, GymMaster-Frontend, 2026-06-28) | 29 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/bd1b040 | Close | Đam | iter2 | bug
Resolve bai tap case-insensitive khi luu giao an | fix(be-pt): resolve bai tap case-insensitive khi luu giao an (commit 3d7ac35, GymMaster-backend, 2026-06-28) | 30 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/3d7ac35 | Close | Như | iter2 | bug | Workout Plan Workspace [SCR-PT-03]
PT check-in flow | Fix PT check-in flow (commit d1b1979, GymMaster-backend, 2026-06-28) | 31 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/d1b1979 | Close | Đam | iter2 | bug
Add PACKAGE_PT_REQUIRED error message | fix(pt-assignment): add PACKAGE_PT_REQUIRED error message (commit 7fbadbe, GymMaster-Frontend, 2026-06-29) | 32 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/7fbadbe | Close | Đam | iter2 | bug | PT Assignment [SCR-ADM-10]
Bo nut quet ma vach (tinh nang demo/mock, khong dung) | fix(fe-nutrition): bo nut quet ma vach (tinh nang demo/mock, khong dung) (commit 6d9f7d9, GymMaster-Frontend, 2026-06-29) | 33 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/6d9f7d9 | Close | Như | iter2 | bug | Meal Journal [SCR-MEM-07]
Chan ghi nhan chi so cho ngay tuong lai + bao loi ro rang | fix(fe-progress): chan ghi nhan chi so cho ngay tuong lai + bao loi ro rang (commit 2e13f83, GymMaster-Frontend, 2026-06-29) | 34 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/2e13f83 | Close | Như | iter2 | bug | Progress [SCR-MEM-06]
Require PT-supporting active membership before PT assignment | fix(assignment): require PT-supporting active membership before PT assignment (commit 02c98ff, GymMaster-backend, 2026-06-29) | 35 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/02c98ff | Close | Đam | iter2 | bug | PT Assignment [SCR-ADM-10]
Ui: reduced text, rework layout of pt workspace | fix ui: reduced text, rework layout of pt workspace (commit c577928, GymMaster-Frontend, 2026-06-30) | 36 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/c577928 | Close | Quang Anh | iter2 | bug
Remove text-to-speech announcement on check-in | fix(fe-checkin): remove text-to-speech announcement on check-in (commit eb7b727, GymMaster-Frontend, 2026-07-01) | 37 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/eb7b727 | Close | Minh | iter3 | bug | Check-in Terminal [SCR-STF-05]
Nhan goi tap theo status BE tra ve, khong hardcode "dang hoat dong" | fix(fe-member360): nhan goi tap theo status BE tra ve, khong hardcode "dang hoat dong" (commit 9af1876, GymMaster-Frontend, 2026-07-13) | 38 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/9af1876 | Close | Lộc | iter4 | bug | Member 360 [SCR-ADM-05]
Profile-360 khong boc don Cancelled lam goi hien tai + gom luat vong doi membership ve MembershipLifecycle | fix(be-part-y): profile-360 khong boc don Cancelled lam goi hien tai + gom luat vong doi membership ve MembershipLifecycle (commit cac3bd4, GymMaster-backend, 2026-07-13) | 39 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/cac3bd4 | Close | Lộc | iter4 | bug | Membership and VNPay [SCR-MEM-02]
Cho 2 test TdeeCalculator cho mutation bat dong bo | fix(test): cho 2 test TdeeCalculator cho mutation bat dong bo (commit 54cc726, GymMaster-Frontend, 2026-07-16) | 40 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/54cc726 | Close | Như | iter4 | bug
Va CVE-2026-49451 - ghim Microsoft.OpenApi 2.7.5 | fix(security): va CVE-2026-49451 - ghim Microsoft.OpenApi 2.7.5 (commit 5c610c2, GymMaster-backend, 2026-07-16) | 41 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/5c610c2 | Close | Như | iter4 | security
MSW start dua voi trang fetch luc mount + them mock VNPay | fix: MSW start dua voi trang fetch luc mount + them mock VNPay (commit a8a7818, GymMaster-Frontend, 2026-07-17) | 42 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/a8a7818 | Close | Như | iter4 | bug
Bang field RDS 7/46 -> 37/46; sua 4 loi lam field bi mat | fix(docs): bang field RDS 7/46 -> 37/46; sua 4 loi lam field bi mat (commit 83acf7a, GymMaster-backend, 2026-07-17) | 43 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/83acf7a | Close | Như | iter4 | documentation
Sua loi im lang lam RDS mat sach bang phan III | fix(docs): sua loi im lang lam RDS mat sach bang phan III (commit f6bc98a, GymMaster-backend, 2026-07-17) | 44 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/f6bc98a | Close | Như | iter4 | documentation
Smoke test dung "/" thay vi /openapi/v1.json | fix(ci): smoke test dung "/" thay vi /openapi/v1.json (commit 9ab3f2f, GymMaster-backend, 2026-07-17) | 45 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/9ab3f2f | Close | Như | iter4 | ci/cd
Don rac markdown trong RDS — Word khong hieu ** va backtick | fix(skills): don rac markdown trong RDS — Word khong hieu ** va backtick (commit 71c8084, GymMaster-backend, 2026-07-17) | 46 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/71c8084 | Close | Như | iter4 | documentation
Chan reps=null cho o Input, tranh canh bao controlled input | fix(pt-training): chan reps=null cho o Input, tranh canh bao controlled input (commit 85c70c6, GymMaster-Frontend, 2026-07-20) | 47 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/85c70c6 | Close | Đam | iter4 | bug | Workout Plan Workspace [SCR-PT-03]
Bo chu 'Buoi tap 1:' hardcode o tieu de giao an dau | fix(pt-training): bo chu 'Buoi tap 1:' hardcode o tieu de giao an dau (commit 409fd38, GymMaster-Frontend, 2026-07-20) | 48 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/409fd38 | Close | Đam | iter4 | bug | Workout Plan Workspace [SCR-PT-03]
Gan SortOrder bai tap theo vi tri list, tranh trung UNIQUE key | fix(pt-training): gan SortOrder bai tap theo vi tri list, tranh trung UNIQUE key (commit 64bbd0e, GymMaster-backend, 2026-07-20) | 49 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/64bbd0e | Close | Đam | iter4 | bug | Workout Plan Workspace [SCR-PT-03]
Sua ten bien Email__* sai trong DEPLOY_GCP + chan commit env.yaml | fix(deploy): sua ten bien Email__* sai trong DEPLOY_GCP + chan commit env.yaml (commit 0339fbd, GymMaster-backend, 2026-07-20) | 50 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/0339fbd | Close | Như | iter4 | ci/cd
Khôi phục quét ảnh món ăn bằng AI | fix(fe-nutrition): khôi phục quét ảnh món ăn bằng AI (commit a3761f4, GymMaster-Frontend, 2026-07-21) | 51 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/a3761f4 | Close | Minh | iter4 | bug | Meal Journal [SCR-MEM-07]
Cập nhật tổng quan | fix(fe-about): cập nhật tổng quan (commit 20a0cb6, GymMaster-Frontend, 2026-07-21) | 52 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/20a0cb6 | Close | Minh | iter4 | bug | About [SCR-COM-01]
Restrict food search to database results | fix(nutrition): restrict food search to database results (commit e923297, GymMaster-Frontend, 2026-07-21) | 53 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/e923297 | Close | Minh | iter4 | bug | Meal Journal [SCR-MEM-07]
Remove synthetic food suggestions | fix(nutrition): remove synthetic food suggestions (commit 6fff6ae, GymMaster-Frontend, 2026-07-21) | 54 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/6fff6ae | Close | Minh | iter4 | bug | Meal Journal [SCR-MEM-07]
Keep meal quantity input focused | fix(nutrition): keep meal quantity input focused (commit 4d05abf, GymMaster-Frontend, 2026-07-21) | 55 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/4d05abf | Close | Minh | iter4 | bug | Meal Journal [SCR-MEM-07]
In Charge lay tu phan cong nhom, khong doan tu git nua | fix(docs): In Charge lay tu phan cong nhom, khong doan tu git nua (commit 5d0ed30, GymMaster-backend, 2026-07-21) | 56 | https://github.com/SWP391-GymMaster/GymMaster-backend/commit/5d0ed30 | Close | Như | iter4 | documentation
Dong bo han don pending 10 -> 30 phut theo backend | fix(fe-billing): dong bo han don pending 10 -> 30 phut theo backend (commit 83e3f4f, GymMaster-Frontend, 2026-07-22) | 57 | https://github.com/SWP391-GymMaster/GymMaster-Frontend/commit/83e3f4f | Close | Lộc | iter4 | bug | Membership Management [SCR-ADM-08]
Revenue report mixes two time zones | The date filter compares against raw UTC (PaymentService.cs:201-208) while the daily grouping converts to Vietnam time (PaymentService.cs:147), so a transaction near the day boundary can be reported under the wrong day. Recorded rather than fixed to avoid a regression close to the defence date. | 58 |  | Open | Lộc | iter4 | bug | Payment Management [SCR-ADM-09]
PaymentService and MembershipPackageService had no unit tests | Coverage measurement showed both service classes at 0 percent. 87 tests were added, raising the suite from 72 to 159 and Billing coverage from 44.5 to 81.6 percent. | 59 |  | Close | Lộc | iter4 | bug | Payment Management [SCR-ADM-09]