## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Welcome / Landing [SCR-AUTH-01] | Public Landing, Role-aware Entry | Guest; all authenticated roles | Public introduction and role-aware entry point. | Minh | Done | iter1 | iter2 | Refined until 2026-06-30
2 | Login [SCR-AUTH-02] | Authenticate Email/Password, Authenticate Google ID Token | Guest | Authenticates the user without a role picker; backend role determines redirect. | Như | Done | iter1 | none
3 | Sign Up [SCR-AUTH-03] | Register Member Account | Guest | Creates a self-service Member account. | Như | Done | iter1 | none
4 | Forgot Password [SCR-AUTH-04] | Send Generic Reset Response and OTP Email | Guest | Requests password-reset OTP by email. | Như | Done | iter1 | none
5 | Reset Password [SCR-AUTH-05] | Reset Password Using OTP | Guest | Verifies six-digit OTP and sets a new password. | Như | Done | iter1 | iter2 | Refined until 2026-06-20
6 | Change Password [SCR-AUTH-06] | Change Password | Admin; Staff; PT; Member | Changes password for the authenticated user. | Như | Done | iter1 | none
7 | About [SCR-COM-01] | Static Content, Public Navigation | Guest; all roles | Displays project/product information and navigation. | Minh | Done | iter1 | iter4 | Refined until 2026-07-21
8 | Admin Dashboard [SCR-ADM-01] | Load Dashboard Summary | Admin | Displays real operational metrics and time-range charts. | Minh | Done | iter1 | iter2 | Refined until 2026-06-28
9 | User Accounts [SCR-ADM-02] | Search/paginate Accounts, Create Account, Update Account/Profile, Lock/unlock, Generate Temporary Password, Soft-delete | Admin | Lists and manages admin/staff user accounts. | Như | Done | iter1 | iter2 | Refined until 2026-06-30
10 | Staff Management [SCR-ADM-03] | List Staff, Create Staff, Update Staff | Admin | Role-filtered staff account workspace. | Như | Done | iter1 | none
11 | Member Management [SCR-ADM-04] | List/search Members, Create Member, Update Member, Soft-delete Member | Admin | Searches and manages Member profiles. | Quang Anh | Done | iter1 | iter2 | Refined until 2026-06-30
12 | Member 360 [SCR-ADM-05] | Load Member 360, Membership History, Payment History | Admin | Aggregates profile, membership, PT, check-ins, progress and nutrition. | Quang Anh | Done | iter1 | none
13 | Member Search and Details [SCR-STF-02] | Search/create Members, Read/update Member, Load Member 360 | Staff | Searches members and displays Member 360 for front-desk work. | Quang Anh | Done | iter1 | none
14 | Trainer Management [SCR-ADM-06] | List Trainers, Create Trainer, Read Trainer, Update Trainer | Admin | Creates, searches and edits PT profiles. | Quang Anh | Done | iter1 | none
15 | Package Management [SCR-ADM-07] | List Packages, Create Package, Update Package | Admin | Creates and edits membership package templates. | Lộc | Done | iter1 | none
16 | Membership Management [SCR-ADM-08] | Paged Memberships, Cancel Membership | Admin | Lists memberships and lifecycle states. | Lộc | Done | iter1 | none
17 | Payment Management [SCR-ADM-09] | Paged Payment History, Payment Summary | Admin | Views payments, summaries and transaction states. | Lộc | Done | iter1 | none
18 | Sell Package [SCR-STF-03] | Create PendingPayment Membership, Confirm Manual Payment | Staff | Guided wizard for creating membership and optional manual payment. | Lộc | Done | iter1 | none
19 | Renew Package [SCR-STF-04] | Renew and Record Payment | Staff | Extends an existing membership and records payment. | Lộc | Done | iter1 | none
20 | Staff Payments [SCR-STF-06] | Payment History, Payment Summary | Staff | Reviews and filters payments for front-desk operations. | Lộc | Done | iter1 | iter4 | Refined until 2026-07-22
21 | Membership and VNPay [SCR-MEM-02] | Active Packages, Membership History, Payment History, Create Pending Request, Create VNPay URL, Cancel | Member | Displays current/history packages and initiates renewal/VNPay payment. | Lộc | Done | iter1 | iter2 | Refined until 2026-06-26
22 | VNPay Return [SCR-MEM-03] | Verify and Return Payment Status | Member / Public callback view | Displays verified payment status after VNPay redirect. | Lộc | Done | iter2 | none
23 | PT Assignment [SCR-ADM-10] | Load Eligible Members, Load Trainer Candidates, Assign Trainer | Admin | Assigns or reassigns trainers to eligible members. | Đam | Done | iter1 | iter2 | Refined until 2026-06-30
24 | Audit Logs [SCR-ADM-11] | Search/filter Audit Logs | Admin | Searches append-only audit records. | Minh | Done | iter1 | none
25 | Admin Profile [SCR-ADM-12] | Load Account, Load/update Personal Profile, Update Name/Phone, Upload Avatar | Admin | Displays and edits Admin account/personal profile. | Như | Done | iter3 | none
26 | Staff Profile [SCR-STF-07] | Account, Personal Profile, Name/phone, Avatar | Staff | Displays and edits Staff account/personal profile. | Như | Done | iter3 | none
27 | PT Profile [SCR-PT-07] | Load Trainer Profile, Name/phone, Personal Data, Avatar | PT | Displays and edits own account/personal profile; specialty is loaded from trainer profile. | Như | Done | iter3 | none
28 | Member Profile [SCR-MEM-09] | Member Profile, Account Name/Phone, Avatar | Member | Displays and edits the member’s account/profile and avatar. | Như | Done | iter3 | none
29 | Staff Dashboard [SCR-STF-01] | Search Members, Payment Summary | Staff | Front-desk launchpad for member search, sales, payments and check-in. | Minh | Done | iter1 | none
30 | Check-in Terminal [SCR-STF-05] | Search Member, Create Check-in, Load Today Records | Staff | Searches or scans a member and performs check-in. | Đam | Done | iter1 | none
31 | PT Check-in [SCR-PT-06] | Member Selection, Check-in, Today List | PT | Checks in assigned members only. | Đam | Done | iter2 | none
32 | PT Dashboard [SCR-PT-01] | Assigned Members, Today Check-ins | PT | Summarizes assigned members and today check-ins. | Minh | Done | iter1 | none
33 | Assigned Members and Member 360 [SCR-PT-02] | Assigned Members, Member 360 | PT | Lists assigned members and displays authorized Member 360. | Quang Anh | Done | iter1 | none
34 | Workout Plan Workspace [SCR-PT-03] | List/create Plans, Update/delete Plan, Exercise Catalog | PT | Creates and maintains workout plans for an assigned member. | Đam | Done | iter1 | none
35 | Trainer Notes Workspace [SCR-PT-04] | List/create Notes, Update/delete Note | PT | Creates and manages dated notes for an assigned member. | Đam | Done | iter1 | none
36 | Workout Plans [SCR-MEM-04] | Load Plans | Member | Read-only list and details of own workout plans. | Đam | Done | iter1 | none
37 | Trainer Notes [SCR-MEM-05] | Load Notes | Member | Read-only timeline of notes written for the member. | Đam | Done | iter1 | none
38 | Member Progress [SCR-PT-05] | Load/record Progress | PT | Records and reviews progress for an assigned member. | Đam | Done | iter1 | none
39 | Progress [SCR-MEM-06] | Load/record Progress | Member | Records own progress and displays charts/history. | Đam | Done | iter1 | none
40 | Member Dashboard [SCR-MEM-01] | Load Aggregate, Optional Self Check-in | Member | Shows current membership, PT, recent activity, progress and nutrition shortcuts. | Minh | Done | iter1 | iter2 | Refined until 2026-06-24
41 | Meal Journal [SCR-MEM-07] | Search/create Food, Read/add Meal, AI Scan, Confirm AI Item | Member | Records meals through food search, custom food or AI image assistance. | Minh | Done | iter1 | iter3 | Refined until 2026-07-01
42 | Calorie Summary [SCR-MEM-08] | Load/save Target, Daily Summary, History | Member | Displays daily calorie/macro target, consumed and history. | Minh | Done | iter1 | iter2 | Refined until 2026-06-24
43 | VNPay IPN Callback | Signature Verification, Amount Check, Idempotent Activation | System | Server-to-server callback from VNPay that verifies the HMAC-SHA512 signature and the amount, then activates the membership. Repeated calls are recorded only once. | Lộc | Done | iter2 | none
44 | Auto-cancel Pending Membership | Lifecycle Rule, 30-minute TTL | System | A pending order left unpaid for 30 minutes is treated as abandoned and set to Cancelled. The deadline is evaluated at read time, with no background job. | Lộc | Done | iter2 | none
45 | Lazy-expire Membership | Lifecycle Rule, Expiry on Read | System | An Active membership past its end date is switched to Expired the moment it is read, and the change is persisted so later reads stay consistent. | Lộc | Done | iter2 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Welcome / Landing [SCR-AUTH-01] | Public Landing, Role-aware Entry | Public introduction and role-aware entry point. | Minh | Done | II | II
2 | Login [SCR-AUTH-02] | Authenticate Email/Password, Authenticate Google ID Token | Authenticates the user without a role picker; backend role determines redirect. | Như | Done | II | II
3 | Sign Up [SCR-AUTH-03] | Register Member Account | Creates a self-service Member account. | Như | Done | II | II
4 | Forgot Password [SCR-AUTH-04] | Send Generic Reset Response and OTP Email | Requests password-reset OTP by email. | Như | Done | II | II
5 | Reset Password [SCR-AUTH-05] | Reset Password Using OTP | Verifies six-digit OTP and sets a new password. | Như | Done | II | II
6 | Change Password [SCR-AUTH-06] | Change Password | Changes password for the authenticated user. | Như | Done | II | II
7 | About [SCR-COM-01] | Static Content, Public Navigation | Displays project/product information and navigation. | Minh | Done | II | II
8 | Admin Dashboard [SCR-ADM-01] | Load Dashboard Summary | Displays real operational metrics and time-range charts. | Minh | Done | II | II
9 | User Accounts [SCR-ADM-02] | Search/paginate Accounts, Create Account, Update Account/Profile, Lock/unlock, Generate Temporary Password, Soft-delete | Lists and manages admin/staff user accounts. | Như | Done | II | II
10 | Staff Management [SCR-ADM-03] | List Staff, Create Staff, Update Staff | Role-filtered staff account workspace. | Như | Done | II | II
11 | Member Management [SCR-ADM-04] | List/search Members, Create Member, Update Member, Soft-delete Member | Searches and manages Member profiles. | Quang Anh | Done | II | II
12 | Member 360 [SCR-ADM-05] | Load Member 360, Membership History, Payment History | Aggregates profile, membership, PT, check-ins, progress and nutrition. | Quang Anh | Done | II | II
13 | Member Search and Details [SCR-STF-02] | Search/create Members, Read/update Member, Load Member 360 | Searches members and displays Member 360 for front-desk work. | Quang Anh | Done | II | II
14 | Trainer Management [SCR-ADM-06] | List Trainers, Create Trainer, Read Trainer, Update Trainer | Creates, searches and edits PT profiles. | Quang Anh | Done | II | II
15 | Package Management [SCR-ADM-07] | List Packages, Create Package, Update Package | Creates and edits membership package templates. | Lộc | Done | II | II
16 | Membership Management [SCR-ADM-08] | Paged Memberships, Cancel Membership | Lists memberships and lifecycle states. | Lộc | Done | II | II
17 | Payment Management [SCR-ADM-09] | Paged Payment History, Payment Summary | Views payments, summaries and transaction states. | Lộc | Done | II | II
18 | Sell Package [SCR-STF-03] | Create PendingPayment Membership, Confirm Manual Payment | Guided wizard for creating membership and optional manual payment. | Lộc | Done | II | II
19 | Renew Package [SCR-STF-04] | Renew and Record Payment | Extends an existing membership and records payment. | Lộc | Done | II | II
20 | Staff Payments [SCR-STF-06] | Payment History, Payment Summary | Reviews and filters payments for front-desk operations. | Lộc | Done | II | II
21 | Membership and VNPay [SCR-MEM-02] | Active Packages, Membership History, Payment History, Create Pending Request, Create VNPay URL, Cancel | Displays current/history packages and initiates renewal/VNPay payment. | Lộc | Done | II | II
22 | PT Assignment [SCR-ADM-10] | Load Eligible Members, Load Trainer Candidates, Assign Trainer | Assigns or reassigns trainers to eligible members. | Đam | Done | II | II
23 | Audit Logs [SCR-ADM-11] | Search/filter Audit Logs | Searches append-only audit records. | Minh | Done | II | II
24 | Staff Dashboard [SCR-STF-01] | Search Members, Payment Summary | Front-desk launchpad for member search, sales, payments and check-in. | Minh | Done | II | II
25 | Check-in Terminal [SCR-STF-05] | Search Member, Create Check-in, Load Today Records | Searches or scans a member and performs check-in. | Đam | Done | II | II
26 | PT Dashboard [SCR-PT-01] | Assigned Members, Today Check-ins | Summarizes assigned members and today check-ins. | Minh | Done | II | II
27 | Assigned Members and Member 360 [SCR-PT-02] | Assigned Members, Member 360 | Lists assigned members and displays authorized Member 360. | Quang Anh | Done | II | II
28 | Workout Plan Workspace [SCR-PT-03] | List/create Plans, Update/delete Plan, Exercise Catalog | Creates and maintains workout plans for an assigned member. | Đam | Done | II | II
29 | Trainer Notes Workspace [SCR-PT-04] | List/create Notes, Update/delete Note | Creates and manages dated notes for an assigned member. | Đam | Done | II | II
30 | Workout Plans [SCR-MEM-04] | Load Plans | Read-only list and details of own workout plans. | Đam | Done | II | II
31 | Trainer Notes [SCR-MEM-05] | Load Notes | Read-only timeline of notes written for the member. | Đam | Done | II | II
32 | Member Progress [SCR-PT-05] | Load/record Progress | Records and reviews progress for an assigned member. | Đam | Done | II | II
33 | Progress [SCR-MEM-06] | Load/record Progress | Records own progress and displays charts/history. | Đam | Done | II | II
34 | Member Dashboard [SCR-MEM-01] | Load Aggregate, Optional Self Check-in | Shows current membership, PT, recent activity, progress and nutrition shortcuts. | Minh | Done | II | II
35 | Meal Journal [SCR-MEM-07] | Search/create Food, Read/add Meal, AI Scan, Confirm AI Item | Records meals through food search, custom food or AI image assistance. | Minh | Done | II | II
36 | Calorie Summary [SCR-MEM-08] | Load/save Target, Daily Summary, History | Displays daily calorie/macro target, consumed and history. | Minh | Done | II | II
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | VNPay Return [SCR-MEM-03] | Verify and Return Payment Status | Displays verified payment status after VNPay redirect. | Lộc | Done | II | II
2 | PT Check-in [SCR-PT-06] | Member Selection, Check-in, Today List | Checks in assigned members only. | Đam | Done | II | II
3 | VNPay IPN Callback | Signature Verification, Amount Check, Idempotent Activation | Server-to-server callback from VNPay that verifies the HMAC-SHA512 signature and the amount, then activates the membership. Repeated calls are recorded only once. | Lộc | Done | II | II
4 | Auto-cancel Pending Membership | Lifecycle Rule, 30-minute TTL | A pending order left unpaid for 30 minutes is treated as abandoned and set to Cancelled. The deadline is evaluated at read time, with no background job. | Lộc | Done | II | II
5 | Lazy-expire Membership | Lifecycle Rule, Expiry on Read | An Active membership past its end date is switched to Expired the moment it is read, and the change is persisted so later reads stay consistent. | Lộc | Done | II | II
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Admin Profile [SCR-ADM-12] | Load Account, Load/update Personal Profile, Update Name/Phone, Upload Avatar | Displays and edits Admin account/personal profile. | Như | Done | II | II
2 | Staff Profile [SCR-STF-07] | Account, Personal Profile, Name/phone, Avatar | Displays and edits Staff account/personal profile. | Như | Done | II | II
3 | PT Profile [SCR-PT-07] | Load Trainer Profile, Name/phone, Personal Data, Avatar | Displays and edits own account/personal profile; specialty is loaded from trainer profile. | Như | Done | II | II
4 | Member Profile [SCR-MEM-09] | Member Profile, Account Name/Phone, Avatar | Displays and edits the member’s account/profile and avatar. | Như | Done | II | II
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document